## Test Plan
Click Here

## TestScenarios
Project Name | Secure Bank
Reference Document
Koli Rani Pal
Creation Date
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the URL in different browsers. | P0 | 1
TS_002 |  | Validate the "Sign up " functionality | P1 | 28
TS_004 |  | Validate the working of the "Login" functionality. | P0 | 5
TS_006 |  | Validate the working of "Create New" functionality. | P1 | 12
TS_006 |  | Validate the working of " Transaction" functionality. | P1 | 2

## TestCase
Product Name |  | SecureBank | TC Start Date | 25/12/2024 | TC Execution Start Date | 26/12/2024 | [5 empty] | TEST CASE
Module Name |  |  | TC End Date | 27/12/2024 | TC Execution End Date | 27/12/2024 | [5 empty] | PASS | 39
Epic |  |  | Test Case Developed By | Koli Rani Pal | Browser (tested) | Yes | [5 empty] | FAIL | 9
Developer Name (TL) |  |  | Test Case Reviewed By | Ehsanul Alam Sabbir | Performance (tested) | [6 empty] | NO RUN | 0
Test Executed by | [11 empty] | BLOCKED | 0
[12 empty] | TOTAL | 48
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Precondition | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Checking by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Mozilla Firefox,Microsoft Edge, Internet Explorer, Opera Mini. | Open the application in any browser. | 1. Go to different browsers. 2. Giving the SecureBank URL in search bar 3. Go to the website. |  |  | Passed
2 |  |  | Sign Up | Verify the page loads successfully without any errors. | Should be load successfully. | Found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. |  |  | Passed
3 |  |  |  | Verify all fields related to Sign Up present on the sign up form. | Should be present the mandatory field . | Found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. check the sign up form's fields. |  |  | Passed
4 |  |  |  | Verify the displayed element are in alignment from. | Elements should be in aligment from. . | Found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3.check the elements alignment. |  |  | Passed
5 |  |  |  | Verify that the form fields are displayed and labeled correctly without spelling mistake. | Should be displayed without any spelling mistake. | Found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. |  |  | Passed
6 |  |  |  | Verify that the Register button is visible, clickable, and styled appropriately. | Should be clickable and visible. | Found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3.click the register button. |  |  | Passed
7 |  |  |  | Verify medatory field are pointed with * or any other sign | Medatory field should be pointed | Not found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Check the mendatory field is pointed with * or not. | not pointed |  | Failed
8 |  |  |  | Verify the I accept the Terms and conditions checkbox is visible and can be selected/unselected. | The checkbox should work properly. | Found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3.click on the I accept the Terms and conditions checkbox . |  |  | Passed
9 |  |  |  | Attempt to submit the form without selecting the checkbox and verify that an error is displayed. | should be an error message | Found as per expectation. | email:email@domain.com password:whoareyou | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Fill all the field with input and try to register without selecting the checkbox . |  |  | Passed
10 |  |  |  | Select the checkbox and verify that the form can proceed to submission. | should register an account. | Found as per expectation. | email:email@domain.com password:whoareyou | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Fill all the field with input and try to register with selecting the checkbox . |  |  | Passed
11 |  |  |  | Verify all the fields of Sign up page should be empty by default. | Fields should be in empty position by default. | Not found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. check all the fields of sign up form is empty or not. | Defect |  | Failed
12 |  |  |  | Verify after refresh the sign up page there should not be any data to the register form. | There should not be any data presented. | Not found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Refresh the sign up page. | refresh |  | Failed
13 |  |  |  | Verify the " Register" button hovering or not. | when hovering the button should be changed the color. | Found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3.check register button is hovering or not. |  |  | Passed
14 |  |  |  | Verify by clicking on the register button for blank input. | Should show massage to fill the blank fields. | Found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3.click on register button without input. |  |  | Passed
15 |  |  |  | Verify that the user can navigate or access the different fields by pressing the ‘Tab’ key on the keyboard. | User should be able to access the different controls by pressing the ‘Tab’ key on the keyboard. | Found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Press tab key from the keyboard to access different input field. |  |  | Passed
16 |  |  |  | Verify users can register successfully by entering valid input.. | Should be able to register new account. | Found as per expectation. | email: email@domain.com password:email123 | Open the application in any browser. | 1. Go to the URL https://www.othoba.com/ 2. Click on the 'Register' button in the right corner. 3.Fill the form with valid inputs. |  |  | Passed
17 |  |  |  | Verify password added by the user should be protected, encrypted, and shown in an asterisk(***). | The password entered should be in encrypted form. | Found as per expected. | password:email123 | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Give input to password field. |  |  | Passed
18 |  |  |  | Verify the password with less then 5 character | Should show an error message | Found as per expectation. | Password:whor | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Fill the password and confirm password field with less then 5 character input. |  |  | Passed
19 |  |  |  | Verify whether an eye icon is added to the password and confirm password field. | There Should be an eye icon | Not found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. check for eye icon inthe password field. | eye icon missing |  | Failed
20 |  |  |  | Verify registration fails if the "Confirm Password" does not match the "Password" field. | There should be an error massage. | Found as per expectation. | password: helloworld confirm password: hello-world | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Fill the password and confirm password field with different input. |  |  | Passed
21 |  |  |  | Enter valid email addresses and verify successful registration. | should accept the email. | Found as per expectation. | email@domain.com | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Fill the email field with valid email. |  |  | Passed
22 |  |  |  | Enter matching passwords in the Password and Confirm Password fields and verify successful input. | Should accept the registration. | Found as per expectation. | password:whoareyou confirm password: whoareyou | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Fill the password and confirm password field with same input. |  |  | Passed
23 |  |  |  | Verify the error message should display after just entering an email address and leaving the password field blank. | Should give an error message | Not found as per expectation. | email: email@domain.com password:email123 | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Left the password and confirm password field without any input and try to register. | error message |  | Failed
24 |  |  |  | Verify the error message should display after just entering a password and leaving the email field blank. | The error message should display after just entering a password | Found as per expectation. | password:whoareyou. | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Fill the password and confirm password field with input. |  |  | Passed
25 |  |  |  | Verify the error message should display after entering an invalid email format. | The error message should display if the email is invalid | Found as per expectation. | rita@.com | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Fill the email field withwrong input. |  |  | Passed
26 |  |  |  | Verify the displayed error message grammar should be correct. | Erro massage should be grammaticaly correct | Found as per expectation. | None | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Give a ivalid email to the email field and check for spelling or gramatical mistake of the error message. |  |  | Passed
27 |  |  |  | Test by trying to register with an already registered email address. | Should be a message saying this email address is already registered. | Not found as per expectation. | email: admin@ssrd.io password:admin | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Fill the email password and confirm password field with already registered input. | wrong message |  | Failed
28 |  |  |  | Verify the user receives a confirmation email after successful registration. | should receive a confirmation email. | Not found as per expectation. | email:juhi@domain.com password:whythis | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Register to an account. | no email. |  | Failed
29 |  |  |  | Inputting only special character as password. | Should not accept the provided input | Found as per expectation. | password:!@#$%^ | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Fill the password and confirm password field with special characters input. |  |  | Passed
30 |  |  | Log in | Varify if it Accept invalid username | Should not accept invalid username | Found as per expected | sadubaba | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Login Button' button in the right corner. 3. Fill the username field with invalid input. |  |  | Passed
31 |  |  |  | check if it accept the wrong password | should not accept wrong password | Found as per expected | email12 | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Login' button in the right corner. 3. Fill the password with wrong input. |  |  | Passed
32 |  |  |  | check if forgot password is working properly or not? | should work properly | Found as per expected |  | Open the application in any browser. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Login' button in the right corner. 3. click the forgot password button |  |  | Passed
33 |  |  |  | check register as a new user is opening a new sign up page or not? | should open a new sign up page to register new account | The sign up page is already filled with old data |  | Open the application in any browser. |  | Filled signup page |  | Failed
34 |  |  |  | Varify if it Accept invalid username | should login the new user | Found as per expected |  | Open the application in any browser. |  |  |  | Passed
35 |  |  | Create New | check the create new button working or not? | The button should be clickable | Found as per expected |  | Open the application in any browser. |  |  |  | Passed
36 |  |  |  | Varify all field are visible | All field should be visible | Found as per expected |  | Open the application in any browser. |  |  |  | Passed
37 |  |  |  | check mendatory field can not be left empty | Show a message to fill those field | Found as per expected |  | Open the application in any browser. |  |  |  | Passed
38 |  |  |  | varify creat button is working | Button should be clickable | Found as per expected |  | Open the application in any browser. |  |  |  | Passed
39 |  |  |  | varify receiver field only accepting valid email | should accept valid email | Found as expected |  | Open the application in any browser. |  |  |  | Passed
40 |  |  |  | varify receiver field do not accept invalid email | should not accept invalid email | Accepting invalid email | email:123@GMHK | Open the application in any browser. |  | Accepting invalid email |  | Failed
41 |  |  |  | Left the Amount field empty | There should be a message to fill the acount field | Found as expected | sender:subu@domain.com receiver:yudu@domain.com | Open the application in any browser. | sender:subu@domain.com receiver:yudu@domain.com |  |  | Passed
42 |  |  |  | varify the transaction date time | should not accept new transaction without filling this field | Found as ecpected |  | Open the application in any browser. |  |  |  | Passed
43 |  |  |  | Varift transaction date time with past and future date | should not create new transaction | Found as expected | 2029-05-06 | Open the application in any browser. |  |  |  | Passed
44 |  |  |  | Varify with negative amount | should give an error | Found as expected | -1 | Open the application in any browser. |  |  |  | Passed
45 |  |  |  | varify with high amount | should not accept the amount | Found as expected | 10000 | Open the application in any browser. |  |  |  | Passed
46 |  |  |  | Left the reason and refernce field empty | There should be no transaction | No message is shown but no transaction happened |  | Open the application in any browser. |  |  |  | Passed
47 |  |  | Transaction | varify transaction field show all the transaction | All the transaction should be visible | Found as per axpected |  | Open the application in any browser. |  |  |  | Passed
48 |  |  |  | Varify the details button working or not | Should show the details of the transaction | Found as per axpected |  | Open the application in any browser. |  |  |  | Passed
49
50
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Secure Bank
Module Name | [5 empty] | Total No. | Status
Feature Name | Sign up
Test Case Version | 1 |  |  |  |  | 39 | PASS
Written By | Koli Rani Pal |  |  |  |  | 9 | FAIL
Executed By | Koli Rani Pal |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | Ehsanul Alam Sabbir |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 39 | 9 | 0 | 0 | 48
Grand Total | 39 | 9 | 0 | 0 | 48
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
Bug Reporting
# SL 01
# SL 06
Issue: Medatory field are not pointed with * or any other sign
Issue: Test by trying to register with an already registered email address.
Reproducing Steps:
1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Check the mendatory field is pointed with * or not. | Reproducing Steps:
Env: Production. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Fill the email password and confirm password field with already registered input.
Module: Register | Env: Production.
Module: Register
Not pointed
Expected:Medatory field should pointed with * or any other sign | Wrong
Responsible QA: Koli Rani Pal | Expected:Already register email should not be accepted
Responsible QA: Koli Rani Pal
Bug Reporting
Bug Reporting
# SL 02
# SL 07
Issue: All the fields of Sign up page is not empty by default.
Issue: Verify the user receives a confirmation email after successful registration.
Reproducing Steps:1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. check all the fields of sign up form is empty or not.
1. Goto the URL https://www.startech.com.bd 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?" | Reproducing Steps:
Env: Production | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Register to an account.
Module: Register | Env: Production.
Module: Register
Defect
Responsible QA: Koli Rani Pal
Not email
Expected:confirmation email should sent
Responsible QA: Koli Rani Pal
Bug Reporting
Bug Reporting
# SL 03
# SL 08
Issue: Verify after refresh the sign up page there should not be any data to the register form.
Reproducing Steps: | Issue: check register as a new user is opening a new sign up page or not?
1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Refresh the sign up page.
4. Click 'Continue'. | Reproducing Steps:
Env: Production. | 1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Check the mendatory field is pointed with * or not.
Module: Register | Env: Production.
Severity: P4 | Module:Login
Resresh
Responsible QA: Koli Rani Pal | Fiiled signup page
Expected:Should open a new signup page
Responsible QA: Koli Rani Pal
Bug Reporting
Bug Reporting
# SL 04
issue:Verify whether an eye icon is added to the password and confirm password field. | # SL 09
Reproducing Steps: | Issue: varify receiver field do not accept invalid email
1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. check for eye icon inthe password field.
Env: Production | Reproducing Steps:
Module: Register
Env: Production.
Eye icon missing | Module: Create New
Responsible QA: Koli Rani Pal
Bug Reporting | Accepting invalid emailfy receiver field do not accept invalid email
Expected:Should not accept invalid email
Responsible QA: Koli Rani Pal
# SL 05
issue: Verify the error message should display after just entering an email address and leaving the password field blank.
Reproducing Steps:
1. Goto the URL http://localhost:1337/ 2. Click on 'Sign up' button in the right corner. 3. Left the password and confirm password field without any input and try to register.
Env: Production
Module:Register
https://prnt.sc/VFuXLpbV-Q_0
Responsible QA: Koli Rani Pal

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (48/48)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/48)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (39/48)*100 = 81%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (9/48)*100 = 19%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/48)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A